## Tabelle1
Variable Costs via Hourly Wages |  |  | Detailed Estimation of Expenditure Time via Work Packages | [6 empty] | Variable Costs Via Work Packages
Role | Hourly Wage | Costs of 150 Hours | Work Packages | Adrian Khairi | Sophie Kirschner | Janin Ahlemeyer | Mika Kuge | Maris Koch | Erika Zhang | Work Packages | Costs
Project Lead | 110 | 16500 | Protocoling | 5 | 0 | 0 | 0 | 0 | 5 | Protocoling | 925
Product Manager | 105 | 15750 | Documents | 30 | 20 | 10 | 5 | 40 | 25 | Documents | 12025
Test Manager | 90 | 13500 | Product analysis | 10 | 25 | 0 | 0 | 0 | 0 | Product analysis | 3725
System Architect | 90 | 13500 | Project design | 0 | 10 | 10 | 30 | 10 | 15 | Project design | 6625
Technical Documentation | 85 | 12750 | Coding | 0 | 20 | 35 | 50 | 40 | 50 | Coding | 16900
Software Developer | 75 | 11250 | Test | 0 | 0 | 50 | 5 | 5 | 5 | Test | 5750
Estimtated Total Variable Costs |  | 83250 | Meetings | 20 | 20 | 20 | 20 | 20 | 20 | Meetings | 11100
|  |  | Customer exchange | 15 | 30 | 0 | 5 | 0 | 0 | Customer exchange | 5250
|  |  | Leading project | 35 | 0 | 0 | 0 | 0 | 0 | Leading project | 3850
|  |  | Presentation | 20 | 0 | 0 | 10 | 0 | 0 | Presentation | 3100
|  |  | Research | 10 | 10 | 10 | 10 | 10 | 10 | Research | 5550
|  |  | GitHub | 5 | 15 | 15 | 15 | 25 | 20 | GitHub | 8450
[10 empty] | Estimtated Total Variable Costs | 83250