## Tabelle1
Variable Costs via Hourly Wages of each Role |  |  |  | Detailed Estimation of Expenditure Time via Work Packages | [5 empty] | Variable Costs Via Work Packages
Role | Team Member | Hourly Wage | Costs of 150 Hours | Work Packages | Adrian Khairi | Janin Ahlemeyer | Mika Kuge | Maris Koch | Erika Zhang | Work Packages | Costs
Project Lead | Adrian Khairi | 110 | 16500 | Protocoling | 5 | 0 | 0 | 0 | 5 | Protocoling | 1075
Product Manager | Erika Zhang | 105 | 15750 | Documents | 30 | 10 | 5 | 40 | 25 | Documents | 10725
Test Manager | Janin Ahlemeyer | 90 | 13500 | Product analysis | 10 | 0 | 0 | 0 | 50 | Product analysis | 6350
System Architect & Software Developer | Mika Kuge | 100 | 15000 | Project design | 0 | 10 | 30 | 10 | 10 | Project design | 5800
Technical Documentation | Maris Koch | 85 | 12750 | Coding | 0 | 35 | 50 | 40 | 10 | Coding | 12600
Estimtated Variable Costs |  |  | 73500 | Test | 0 | 50 | 5 | 5 | 0 | Test | 5425
|  |  |  | Meetings | 20 | 20 | 20 | 20 | 20 | Meetings | 9800
|  |  |  | Customer exchange | 15 | 0 | 5 | 0 | 0 | Customer exchange | 2150
|  |  |  | Leading project | 35 | 0 | 0 | 0 | 0 | Leading project | 3850
|  |  |  | Presentation | 20 | 0 | 10 | 0 | 0 | Presentation | 3200
|  |  |  | Research | 10 | 10 | 10 | 10 | 10 | Research | 4900
|  |  |  | GitHub | 5 | 15 | 15 | 25 | 20 | GitHub | 7625
[10 empty] | Estimtated Variable Costs | 73500